## Summary
Project Name | : | Demo Evershop
Project Manager | : | Hridoy Dash
Project ID | : | Ostad101
Tester | : | Md. Tahsin Islam Molla
Test Case Preparation Date | : | 30 January, 2025
Version | : | 0.01
website |  | https://demo.evershop.io/
Test scenario | : | Search functionality
Total Test case | : | 28
Total Passed test case | : | 12
Total Failed test case | : | 11
Not Implemented Test Case | : | 5
Total untested | : | 0

## TestCases
Test Case ID | Preconditions | Priority | Section | Steps | Data | Expected Result | Actual Result | Status | Defects
TC_01 | Search functionality is enabled and data is indexed | Critical | Search functionality | 1. Enter a product name in the search bar. 2. Press Enter. | Product name: "Nike Air" | Relevant products with the brand "Nike Air" should be displayed | Found as expected | Pass
TC_02 | Search functionality is enabled and data is indexed | Critical | Search functionality | 1. Enter a partial keyword. 2. Press Enter | Partial keyword: "air" | Results should display products containing "air"(e.g. "Nike Air".) | Found as expected | Pass
TC_03 | Search functionality is enabled and data is indexed | Critical | Search functionality | 1. Enter a typo in the search bar. 2. Press Enter. | Typo: "Nike Aor" | Results should display products matching "Nike Air" using fuzzy search. | message is shown 'There is no product to display' | Fail | https://prnt.sc/-yWh4BcdfNF1
TC_04 | Search functionality is enabled and data is indexed | Critical | Search functionality | 1. Enter a synonym in the search bar. 2. Press Enter. | Synonym: "trainers" | Results should display products matching "sneakers." | message is shown 'There is no product to display' | Fail | https://prnt.sc/_Jg_6RBx8RhW
TC_05 | Search functionality is enabled and data is indexed | Critical | Search functionality | 1. Start typing in the search bar. | Typed text: "Nike" | Real-time suggestions should appear (e.g., "Nike Air," "Nike Running Shoes"). | Found as expected | Pass
TC_06 | Search functionality is enabled and data is indexed | Critical | Search functionality | 1. Perform a search. 2. Apply filters (e.g., price range, brand). | Filters: Price range $50-$100, Brand: Nike | Results should display products within the price range and brand. | message is shown 'There is no product to display' | Pass
TC_07 | Search functionality is enabled and data is indexed | Critical | Search functionality | 1. Perform a search. 2. Sort results by popularity. | Sort by: Popularity | Results should be sorted by popularity (e.g., most viewed/purchased first) | message is shown 'There is no product to display' | Fail | https://prnt.sc/mGHHLccyFZez
TC_08 | Search functionality is enabled and data is indexed | Critical | Search functionality | 1. Perform a search on mobile. | Search term: "Nike Air" | Search bar should be optimized for mobile. | Found as expected | Pass
TC_09 | Search functionality is enabled and data is indexed | Medium | Search functionality | 1. Perform a search with no matching results. | Search term: "InvalidProduct123" | Display "No results found" message or suggest similar products. | Found as expected | Pass
TC_10 | Search functionality is enabled and data is indexed | Medium | Search functionality | 1. Perform a search. | Search term: "Nike Air" | Results should load within 1-2 seconds (instant search). | Found as expected | Pass
TC_11 | Search functionality is enabled and data is indexed | Medium | Search functionality | 1. Use voice search. | Voice input: "Find Nike Air" | Results should display products matching "Nike Air." |  | Not Implemented
TC_12 | Search functionality is enabled and data is indexed | Lower | Search functionality | 1. Use image search. | Image: Photo of a Nike Air shoe | Results should display products matching the image. |  | Not Implemented
TC_13 | Search functionality is enabled and data is indexed | Lower | Search functionality | 1. Access search analytics dashboard. | N/A | Display insights (e.g., most searched keywords, failed searches). |  | Not Implemented
TC_14 | Search functionality is enabled and data is indexed | Lower | Search functionality | 1. Enter a product SKU(Stock Keeping Unit) in the search bar. 2. Press Enter. | SKU: "12345" | Results should display the exact product matching the SKU. | message is shown 'There is no product to display' | Fail | https://prnt.sc/cpDUFEVtYdfP
TC_15 | Search functionality is enabled and data is indexed | Critical | Search functionality | 1. Enter a product category in the search bar. 2. Press Enter. | Category: "Running Shoes" | Results should display products under the "Running Shoes" category. | message is shown 'There is no product to display' | Fail | https://prnt.sc/QMEYgOio38aE
TC_16 | Search functionality is enabled and data is indexed | Critical | Search functionality | 1. Enter a brand name in the search bar. 2. Press Enter. | Brand: "Adidas" | Results should display products from the "Adidas" brand. | message is shown 'There is no product to display' | Fail | https://prnt.sc/CGK0ShdOKaK5
TC_17 | Search functionality is enabled and data is indexed | Critical | Search functionality | 1. Enter a color in the search bar. 2. Press Enter. | Color: "Red" | Results should display products available in "Red." | message is shown 'There is no product to display' | Not Implemented | https://prnt.sc/fu8zMAeN1jjT
TC_18 | Search functionality is enabled and data is indexed | Critical | Search functionality | 1. Enter a size in the search bar. 2. Press Enter. | Size: "10" | Results should display products available in size "10." | message is shown 'There is no product to display' | Fail | https://prnt.sc/zDaee3cJkQdJ
TC_19 | Search functionality is enabled and data is indexed | Critical | Search functionality | 1. Enter a price range in the search bar. 2. Press Enter. | Price range: "$50-$100" | Results should display products within the price range of $50-$100. | message is shown 'There is no product to display' | Not Implemented
TC_20 | Search functionality is enabled and data is indexed | Critical | Search functionality | 1. Enter a keyword with special characters. 2. Press Enter. | Keyword: "#Nike Air" or, #Phantom | Results should display products matching "#Nike Air,or, #Phantom | Found as expected | Pass | https://prnt.sc/X5rHXDiheICq
TC_21 | Search functionality is enabled and data is indexed | Critical | Search functionality | 1. Perform a search on desktop. | Search term: Nike Air | Search bar should be optimized for desktop (e.g., larger UI elements). | Found as expected | Pass
TC_22 | Search functionality is enabled and data is indexed | Medium | Search functionality | 1. Perform a search with no matching results. 2. Check suggestions. | Search term: "InvalidProduct123" | Suggest similar products or related searches (e.g., "Did you mean Nike Air Max?"). | message is shown 'There is no product to display' | Fail | https://prnt.sc/zu0SZ2uUhZZL
TC_23 | Search functionality is enabled and data is indexed | Medium | Search functionality | 1. Perform a search. 2. Check for caching behavior. | Search term: "Nike Air" | Repeated searches for the same term should load faster due to caching. | Found as expected | Pass
TC_24 | Search functionality is enabled and data is indexed | Medium | Search functionality | 1. Perform a search. 2. Check for pagination. | Search term: "Shoes" | Results should be paginated if they exceed a certain number (e.g., 20 per page). | Found as expected | Pass
TC_25 | Search functionality is enabled and data is indexed | Lower | Search functionality | 1. Use barcode search. | Barcode: "NJC93155" | Results should display the product matching the barcode. | message is shown 'There is no product to display' | Fail | https://prnt.sc/s6e4HStpptaA
TC_26 | Search functionality is enabled and data is indexed | Lower | Search functionality | 1. Perform a search. 2. Check for multilingual support. | Search term: "Zapatillas" (Spanish for "Sneakers") , ফ্যান্টম | Results should display products matching "Sneakers." | message is shown 'There is no product to display' | Fail | https://prnt.sc/kYJCb09BNEC9
TC_27 | Search functionality is enabled and data is indexed | Lower | Search functionality | 1. Enter an empty search query. 2. Press Enter. | Search term: "" | Display blank message or, please enter a search term or, show popular products. | Found as expected | Pass
TC_28 | Search functionality is enabled and data is indexed | Critical | Search functionality | 1. Enter a very long search query. 2. Press Enter. | Search term: "Nike Air Max 2023 Limited Edition Running Shoes..." | Results should display products matching the long query. | message is shown 'There is no product to display' | Fail | https://prnt.sc/UlJIWXHfFIH2